## ACME Sprint Planner & Tracker
Sprint Planning and Tracking
PROJECT TITLE |  | Flight Ticket Booking Application
PROJECT MANAGER |  | Shreyash Pawar
COMPANY NAME |  | Simpli Learn
DATE |  | 4/11/2022
PLANNER & TRACKER
Sprint 1
Sprint 2
TASK | TASK | TASK | AMOUNT OF WORK IN HOURS |  |  | STORY | START | DUE | DURATION | STATUS | PCT OF TASK | WEEK 1 |  |  |  | WEEK 2
ID | NAME | OWNER | ESTIMATE | COMPLETED | REMAINING | POINTS | DATE | DATE |  |  | COMPLETE | S | M | T | W | T | F | S | S
| SPRINT #1 | Shreyash Pawar | 10 | 10 | 0 | 4 | 2022-04-03 | 2022-04-06 | 4 | Completed | 100%
1 | Analysis Finished | Shreyash Pawar | 1 | 1 | 0 |  | 2022-04-03 | 2022-04-03 | 1 | Completed | 100%
2 | UI for Application | Shreyash Pawar | 3 | 3 | 0 |  | 2022-04-04 | 2022-04-04 | 1 | Completed | 100%
3 | Login/Log Out Functionality | Shreyash Pawar | 3 | 3 | 0 |  | 2022-04-05 | 2022-04-05 | 1 | Completed | 100%
4 | Create New User/Password Reset | Shreyash Pawar | 3 | 3 | 0 |  | 2022-04-06 | 2022-04-06 | 1 | Completed | 100%
| SPRINT #2 | Shreyash Pawar | 10 | 10 | 0 | 4 | 2022-04-07 | 2022-04-10 | 4 | Completed | 100%
5 | Search Flight & Flight Booking | Shreyash Pawar | 3 | 3 | 0 |  | 2022-04-07 | 2022-04-07 | 1 | Completed | 100%
6 | Add Flight & Delete Flight | Shreyash Pawar | 3 | 3 | 0 |  | 2022-04-08 | 2022-04-08 | 1 | Completed | 100%
7 | View All Locations & Session Management | Shreyash Pawar | 2 | 2 | 0 |  | 2022-04-09 | 2022-04-09 | 1 | Completed | 100%
8 | Documentation | Shreyash Pawar | 2 | 2 | 0 |  | 2022-04-10 | 2022-04-10 | 1 | Completed | 100%